## Sheet1
student Id | Student Name | Project name | Year
s260598 | Surendra Panday | PRT585 Professional Project | 2020
Individual Activity flow
|  |  |  | Date | Time | Duration in hour | Activity | Issue | Resolution
|  |  |  | 2020-08-14 | 7pm to 8pm | 1 | Created github account with team's project, course material reading, | No issues | N/A
|  |  |  | 2020-08-15 | 4pm to 6pm | 1 | Chat with team member to add team members in Github, find and add team members in github account | no issues | N/A
|  |  |  | 2020-08-15 | 6am to 8 am | 1 | Creation of .net mvc core project, run project, | Complexity in doing .NET work in iMac in general | N/A
|  |  |  | 2020-08-15 | 8 am to 10am | 2 | Adding data layer of Book, printer and adding validation logic on respective classes | no issues | N/A
|  |  |  | 2020-08-15 | 10am to 2pm | 2 | Installation of entity framework, sqlite, creation of database with Book, and Printer tables | no issues | no resoution
|  |  |  | 2020-08-15 | 2pm to 4pm | 2 | Docker installation on iMac, and configuration for better performance | complexity around setup in iMac for database | used docker to overcome
|  |  |  | 2020-08-15 | 4pm to 6pm | 2 | Installation of mssql server , configuration on visual studio code to run mssql server on docker | complexity in setup of mssql on docker | followed microsoft guidelines
|  |  |  | 2020-08-16 | 6pm to 7pm | 1 | Installation of Azure
|  |  |  | 2020-08-16 | 8pm 11pm | 3 | Created MSSQL servers, database connection vida docker, docker resetup for iMac to use Azure Data Studio | complexity around docker/kubernete | followed blogs, online learning
|  |  |  | 2020-08-17 | 6am to 12am | 6 | Created additional scanner class, migrate data, update database, connect to SQL, and troublehoot | confusion around migration after first migration | restarted migration to replace initial one
|  |  |  | 2020-08-18 | 12 to 2pm | 2 | Re-migration of data, connection to localhost SQL server, and update database | Confusion around how Visual studio mssql servername | Used localhost as database on iMac
|  |  |  | 2020-08-18 | 6pm to 10pm | 4 | Creating additional columns, troubleshooting nullpointer exception on view, updating fields, List structure, reading | How the view understands Listed item to be displayed | Working through to fix data structure
|  |  |  | 2020-08-18 | 6 am to 12pm | 6 | Troubleshooting view not displaying correctly, using SeedData instead of data from database | Null parameter | working for fix
[5 empty] | Total hours | 33
Team's activity timesheet
Attendees on group discussion
|  | Surendra Panday |  | Date | Time | Duration | Activity | Issue | Resolution
|  |  |  | 2020-08-15 | 5pm to 7pm | 2 | Team discussion on MVC .NET, project topics individually | No issues
|  | Mayur Dineshbhai Vaghasiya |  | 2020-08-15 | 4pm to 6pm | 2 | Creation of database , populate fields | No issues
|  |  |  | 2020-08-16 | 2pm to 4pm | 2 | code debugging and fixing dependency issues in .net mvc | no issues
|  |  |  | 2020-08-17 | intermittently | 2 | Sharing knowledge on troubleshooting step of database migration | no issues
Kinnary Jaydeep
[5 empty] | Total hours | 8