## Sheet1
student Id | Student Name | Project name | Year
s260598 | Surendra Panday | PRT585 Professional Project | 2020
Individual Activity flow
|  |  |  | Date | Time | Duration in hour | Activity | Issue | Resolution
|  |  |  | 2020-08-19 | 7pm to 8pm | 1 | Reading on Angular 5, 6 | No issues | N/A
|  |  |  | 2020-08-19 | 4pm to 6pm | 1 | Reading on Angular 7, 8 | No issues | N/A
|  |  |  | 2020-08-20 | 6am to 8 am | 1 | Reading on Angular 8 | Complexity in doing .NET work in iMac in general | N/A
|  |  |  | 2020-08-20 | 8 am to 10am | 2 | Reading on Angular 9 | no issues | N/A
|  |  |  | 2020-08-21 | 10am to 2pm | 2 | Creating .NET MVC project | no issues | N/A
|  |  |  | 2020-08-21 | 2pm to 4pm | 1 | Add angular component | complexity around setup in iMac for database | N/A
|  |  |  | 2020-08-22 | 4pm to 6pm | 2 | Add service with some methods | complexity in setup of mssql on docker | N/A
|  |  |  | 2020-08-22 | 6pm to 7pm | 1 | Add Controller to fetch employees |  | N/A
|  |  |  | 2020-08-23 | 8pm 11pm | 2 | Create database and table for employee | complexity around docker/kubernete | N/A
|  |  |  | 2020-08-23 | 6am to 12am | 2 | Connection string work and logic in controller | confusion around migration after first migration | N/A
|  |  |  | 2020-08-24 | 12 to 2pm | 2 | Reading on weekly material | Confusion around how Visual studio mssql servername | N/A
[5 empty] | Total hours | 17
Team's activity timesheet
Attendees on group discussion
|  | Surendra Panday |  | Date | Time | Duration | Activity | Issue | Resolution
|  |  |  | 2020-08-19 | 5pm to 7pm | 2 | Discussion on Angular, teams individual canvass | No issues
|  | Mayur Dineshbhai Vaghasiya |  | 2020-08-21 | 4pm to 6pm | 2 | Discussion on Angular, troubleshooting errors on code | No issues
|  |  |  | 2020-08-23 | 2pm to 4pm | 2 | Rediscuss canvas, angular, and weekly learning topics from learnline | no issues
Kinnary Jaydeep
[5 empty] | Total hours | 6