## Sheet1
student Id | Student Name | Project name | Year
s260598 | Surendra Panday | PRT585 Professional Project | 2020
Individual Activity flow
|  |  |  | Date | Time | Duration in hour | Activity | Issue | Resolution
|  |  |  | 2020-08-24 | 7pm to 8pm | 1 | Reading on how agular works with .NET project together | No issues | N/A
|  |  |  | 2020-08-26 | 4pm to 6pm | 1 | Trying out a simple angular project and running locally | No issues | N/A
|  |  |  | 2020-08-27 | 6am to 8 am | 1 | Angular downgrade from 10 to 8 | command failures | restart computer
|  |  |  | 2020-08-27 | 8 am to 10am | 2 | Writing tasks that teamn needs to do and assigning people | no issues | N/A
|  |  |  | 2020-08-29 | 10am to 2pm | 2 | Designing different pages usign wireframe website | no issues | N/A
|  |  |  | 2020-08-29 | 2pm to 4pm | 3 | Adding angular components for 4 to 5 pages | no issues | N/A
|  |  |  | 2020-08-29 | 4pm to 6pm | 2 | Adding footer on free item application and realigning links | no issues | N/A
|  |  |  | 2020-08-29 | 6pm to 7pm | 1 | Add introductory text and fixing routing for all pages | no issues | N/A
|  |  |  | 2020-08-30 | 8pm 11pm | 2 | Trying out angular material library and switching off due to issues with version | no issues | N/A
|  |  |  | 2020-08-30 | 6am to 12am | 2 | Connection string work and logic in controller | no issues | N/A
|  |  |  | 2020-08-30 | 12 to 2pm | 2 | Reading on weekly material | no issues | N/A
[5 empty] | Total hours | 19
Team's activity timesheet
Attendees on group discussion
|  | Surendra Panday |  | Date | Time | Duration | Activity | Issue | Resolution
|  |  |  | 2020-08-25 | 5pm to 7pm | 2 | Discussion and finalisation of project, feature, sprint and list of features | No issues | N/A
|  | Mayur Dineshbhai Vaghasiya |  | 2020-08-26 | 4pm to 8pm | 4 | Running project, troubleshooting, guiding on angular project | No issues | N/A
|  |  |  | 2020-08-27 | 2pm to 4pm | 2 | Rediscuss the progress of task and troubleshoot team's problem | No issues | N/A
Kinnary Jaydeep
[5 empty] | Total hours | 8